## Slide 1
PVH – B2B Automation Scope & Milestones
Badhurudeen S
Test Architect

## Slide 2: Outline
Objective
B2B Store for automation
Automation Scope
Target Browsers
Tasks & Deliverables
Milestones & Deliveries
Staffing Plan

## Slide 3: Objective
The objective of this engagement is to perform automation testing on PVH B2B stores
Our testing focuses 6 stores of PVH
Create automation suite
  Smoke suite
  Regression suite

## Slide 4: B2B Stores for automation
Feasible for automation
  Speedo B2B US Store
  Speedo B2B Canada Store
  PVH Direct
  Speedo B2B Coaches
  Corporate Outfitters USA Store
  Corporate Outfitters Canada Store
  Earlier, we committed 27% of Overall B2B test cases for automation which covers 4 stores
  After reviewing the test cases, we regroup and reuse test cases which covers 6 stores
  Current automation coverage is 35%.

## Slide 5: Automation Scope
Registration
Sign-in page
Logoff
Forgot Password
My Account
Header & Footer
Search
Add to Bag
PDP
Shopping Cart
Manage Saved Orders
Checkout
Shipping Page
Order History
Promotion Code
Error
Help

## Slide 6: Target Browsers
Browser Compatibility:
 | Browser | Version | Operating System | Priority
 | Chrome | 54 | Win 7/OSX | High
 | Internet Explorer | 11 | Win 7 | High
 | Safari | 10 | OSX | High

## Slide 7: Tasks & Deliverables
Tasks:
Automation Feasibility Study
Test Scripts Development
Test Scripts Verification
Review & Fixes
Deliverables:
Automation Test Plan
Sprint wise Demos
Test Execution Status Reports

## Slide 8: Milestones & Deliveries
Dates are as per Latest B2B Functional Testing Plan
 | Sets | Sprints | Duration | Start Date | End Date | Deliveries | 
 | Set 1 | Sprint 2 | 1 Week | 2-Jan | 8-Jan | Environment Setup Page Object Extraction | 
 |  | Sprint 3 | 4 Weeks | 9-Jan | 5-Feb | Page Object Extraction Create re-usables of Smoke Tests Smoke suite creation | 
 | Set 2 | Sprint 4 & SIT Closure 1 | 3 Weeks | 6-Feb | 26-Feb | Page Object Extraction Create re-usables of Regression Tests Regression suite creation (40%) | 
 |  | SIT Closure 2 | 2 Weeks | 27-Feb | 12-Mar |  | 
 | Set 3 | UAT, Pre Launch & Post Launch | 4 Weeks | 13-Mar | 9-Apr | Regression suite creation (80%) | 
 | Set 4 | Maintenance | 3 Weeks | 10-Apr | 30-Apr | Regression suite creation (100%) Final execution and update the suite | 

## Slide 9: Staffing Plan
Automation Script Development:
 | S.No | Role | Sprint - 2 | Sprint - 3 |  |  |  | Sprint – 4/SIT Closure 1 |  |  | SIT Closure 2 |  | UAT/ Pre Launch & Post Launch |  |  |  | Maintenance |  |  | Total Hours | 
 |  |  | 2-Jan | 9-Jan | 16-Jan | 23-Jan | 30-Jan | 6-Feb | 13-Feb | 20-Feb | 27-Feb | 6-Mar | 13-Mar | 20-Mar | 27-Mar | 3-Apr | 10-Apr | 17-Apr | 24-Apr |  | 
 | 1 | Automation Test Lead | 20 Hrs. | 20 Hrs. | 40 Hrs. | 32 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 32 Hrs. | 40 Hrs. | 620 | 
 | 2 | Automation Test Engineer |  |  | 24 Hrs. | 32 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 32 Hrs. | 40 Hrs. | 604 | 
 | 3 | Automation Test Engineer |  |  | 24 Hrs. | 32 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 40 Hrs. | 32 Hrs. | 40 Hrs. | 536 | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1760 |