## Slide 1
PVH – WCS8 – Automation Weekly Status Report
Tamilarasan Sekar
Consultant, QA

## Slide 2: Week 1 : 7th Nov
Feasibility Study on converting Manual Regression Suite to Automation Scripts
Capturing Page Objects for all three sites
  Calvin Klein
  Tommy Hilfiger
  Speedo
Reviewing Sprint-3 Manual Test Design - In progress
Reusable Script Authoring - Started
  Working on Header, Category pages for CK Site

## Slide 3: Week 2 : 14th Nov
Actual Completion :
Page Object Capturing - 100 % Completed
Reusable Script Authoring - 18 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 0 % Completed
  Script Authoring will initiate once reusable script authoring is done
Expected Projection on Next Week :
Reusable Script Authoring - 30-35 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 0 % Completed

## Slide 4: Week 3 : 21th Nov
Actual Completion :
Page Object Capturing - 100 % Completed
Reusable Script Authoring - 30 % Completed
  Reusable Script Authoring is continuing in CK Site
  Converting CK Scripts into TH & SP (Specifying the conditions for other Sites)
Script Authoring - 1 % Completed
  Starting with end to end flow – Checkout Scenarios
Expected Projection for Next Week :
Reusable Script Authoring - 45-50 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 7 % Completed
  Adding Scripts for helping on Smoke Testing

## Slide 5: Week 4 : 30th Nov
Actual Completion :
Page Object Capturing for Desktop Browser - 100 % Completed
Page Object Capturing for Mobile Browser – Initiated
Reusable Script Authoring - 45 % Completed
  Reusable Script Authoring is continuing in CK Site
  Converting CK Scripts into TH & SP (Specifying the conditions for other Sites)
Script Authoring - 15 % Completed
  Completed 13 Script Out of 81
Expected Projection for Next Week :
Reusable Script Authoring - 60 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 23 % Completed
  Adding Scripts for helping on Smoke Testing
Complete Page Object Extraction for Mobile Browsers

## Slide 6: Week 4 : 08th Dec
Actual Completion :
Page Object Capturing for Desktop Browser - 100 % Completed
Page Object Capturing for Mobile Browser – 1% Completed
Reusable Script Authoring - 55 % Completed
  Reusable Script Authoring is continuing in TH & SP Site
  Converting CK Scripts into TH & SP (Specifying the conditions for other Sites)
Script Authoring - 29 % Completed
  Completed 24 Script Out of 81
 | Total Scripts | Completed Scripts | Remaining Scripts
Regression | 66 | 17 | 49
CSR Orders | 15 | 7 | 8

## Slide 7
Expected Projection for Next Week :
Reusable Script Authoring - 70 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 32 % Completed
  Adding Scripts for helping on Smoke Testing
Complete Page Object Extraction for Mobile Browsers
Target :
  Working on Order Placing Scenarios
Status Cont..
  Data Requirement :
  Test Data for Loyalty User accounts
  Gift Card Details

## Slide 8
 |  |  | Desktop |  | Mobile |  | CSR | 
Phase Details | Start Date | End Date | Planned Script Development | Actual Completed Scripts | Planned Script Development | Actual Completed Scripts | Planned Script Development | Actual Completed Scripts
Sprint 4 | 31-Oct | 23-Dec | 20 | 17 | - | - | 15 | 7
Sprint 5 | 26-Dec | 20-Jan | 14 |  | 10 |  | - | -
UAT & Performance | 23-Jan | 10-Mar | 20 |  | 27 |  | - | -
Prep Launch | 13-Mar | 7-Apr | 12 |  | 17 |  | - | -
Post Launch | 10-Apr | 12-May | - |  | 12 |  | - | -
 |  |  | 66 | 17 | 66 | 0 | 15 | 7
PVH B2C Automation – Milestone :
Complete Milestone Plan Sheet :
* Start and End Dates are as per Sprint Plan

## Slide 9: Week 5 : 14th Dec
Actual Completion :
Page Object Capturing for Desktop Browser - 100 % Completed
Page Object Capturing for Mobile Browser – 20% Completed
Reusable Script Authoring - 60 % Completed
  Reusable Script Authoring is continuing in TH & SP Site
  Converting CK Scripts into TH & SP (Specifying the conditions for other Sites)
Desktop Site - Script Authoring - 33 % Completed
  Completed 29 Script Out of 81
 | Total Scripts | Completed Scripts | Remaining Scripts
Regression | 66 | 19 | 47
CSR Orders | 15 | 10 | 5

## Slide 10
Expected Projection for Next Week :
Reusable Script Authoring - 70 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 40 % Completed
  Adding Scripts for helping on Smoke Testing
Complete Page Object Extraction for Mobile Browsers
Target :
  Working on Order Placing Scenarios
Status Cont..
  Data Requirement :
  Test Data for Loyalty User accounts – Completed
  Gift Card Details
  Blockers :
  Shopper runner link issue – Which is breaking 2 Checkout Scenarios
  Loyalty Modules

## Slide 11: Week 6 : 21st Dec
Actual Completion :
Page Object Capturing for Desktop Browser - 100 % Completed
Page Object Capturing for Mobile Browser – 45% Completed
Reusable Script Authoring - 70 % Completed
Desktop Site - Script Authoring - 41 % Completed
  Completed 33 Script Out of 81
This week we are concentrating on Mobile Site and Capturing all the page objects
Start with Mobile Reusable Script Authoring
 | Total Scripts | Completed Scripts | Remaining Scripts
Regression | 66 | 23 | 43
CSR Orders | 15 | 10 | 5

## Slide 12
Expected Projection for Next Week :
Reusable Script Authoring - 70 % Completed
  Reusable Script Authoring is continuing in CK Site
  Creating the individual Scripts for each scenario that we are going to cover the regression
Script Authoring - 45 % Completed
  Adding Scripts for helping on Smoke Testing
Mobile Script Authoring – 2 % Completed
Execute the scripts all at once
Status Cont..
  Data Requirement :
  Gift Card Details
  Blocker Module :
  Loyalty Modules

## Slide 13
Scenario Cover :
Google Chrome
CK
SP
TH
Shop Runner Checkout
OneSource
Reusable Functions
Reusable Functions
Pass
Pass
Fail

## Slide 14: DEMO

## Slide 15
Working flow diagram :
Internet Explorer
Google Chrome
Safari
Edge
CK
SP
TH
CK
SP
TH
CK
SP
TH
CK
SP
TH
Test Scripts
OneSource
Browsers
Sites
Reusable Function
Reusable Function

## Slide 16: Week 7 : 28th Dec
Actual Completion :
Page Object Capturing for Desktop Browser - 100 % Completed
Page Object Capturing for Mobile Browser – 60% Completed
Reusable Script Authoring - 70 % Completed
Desktop Site – Script Authoring – 46 % Completed
  Completed 37 Scripts Out of 81
Mobile Site - Script Authoring - 5 % Completed
  Completed 4 Script Out of 81
This week we are concentrating on Mobile Site and Capturing all the page objects
Start with Mobile Reusable Script Authoring
 |  | Total Scripts | Completed Scripts | Remaining Scripts | 
 | Regression - Browser | 81 | 37 | 44 | 
 | Regression - Mobile | 81 | 4 | 77 | 
 | CSR Orders | 15 | 10 | 5 | 

## Slide 17
Expected Projection for Next Week :
Reusable Script Authoring - 70 % Completed
Script Authoring - 50 % Completed
  Adding Scripts for helping on Smoke Testing
Mobile Script Authoring – 8 % Completed
Execute the scripts all at once
Status Cont..
  Working Modules:
  Loyalty Modules and Mobile Script Authoring

## Slide 18: Week 8 : 04th Jan – B2C Automation
Actual Completion :
Page Object Capturing for
  Desktop Browser - 100 % Completed
  Mobile Browser – 60% Completed
Reusable Script Authoring for
  Desktop Browser - 70 % Completed
  Mobile Browser – 20% Completed
Desktop Site – Script Authoring – 50 % Completed
  Completed 41 Scripts Out of 81
Mobile Site - Script Authoring - 12 % Completed
  Completed 10 Script Out of 81
This week we are concentrating on Mobile Site and Capturing all the page objects
Start with Mobile Reusable Script Authoring
 |  | Total Scripts | Completed Scripts | Remaining Scripts | 
 | Regression - Desktop | 81 | 41 | 40 | 
 | Regression - Mobile | 81 | 10 | 71 | 
 | CSR Orders | 15 | 10 | 5 | 

## Slide 19
Expected Projection for Next Week :
Reusable Script Authoring - 70 % Completed
Script Authoring - 55 % Completed
  Adding Scripts for helping on Smoke Testing
Mobile Script Authoring – 17 % Completed
Execute the scripts all at once
Status Cont..
  Working Modules:
  Loyalty Modules
    Waiting for Loyalty functionality to be stable for automating
  Mobile Script Authoring
    Modules
      Checkout
      Gift box
      Add to bag

## Slide 20: Week 8 : 04th Jan – B2B Automation
Status :
Page Object Capturing
  Speedo US – In Progress
  Speedo Canada - In Progress
  Speedo Coaches (Yet to start)
Next :
Remaining 3 Sites are not stable in terms of functionalities
  PVH direct
  PVH Corporate Outfitters US
  PVH Corporate Outfitters Canada

## Slide 21: Week 9 : 11th Jan – B2C Automation
Actual Completion :
Page Object Capturing for
  Desktop Browser - 100 % Completed
  Mobile Browser – 65% Completed
Reusable Script Authoring for
  Desktop Browser - 75 % Completed
  Mobile Browser – 30 % Completed
Desktop Site – Script Authoring – 52 % Completed
  Completed 42 Scripts Out of 81
Mobile Site - Script Authoring - 17 % Completed
  Completed 14 Script Out of 81
Weekly Task:
  Mobile Script Authoring
  Desktop Browser Dry Run
  Regression help with Manual Team
Working on Mobile Reusable Script Authoring

## Slide 22
Expected Projection for Next Week :
Reusable Script Authoring - 75 % Completed
Script Authoring - 57 % Completed
  Adding Scripts for helping on Smoke Testing
  Adding Script Execution for Sprint-4 Regression
Mobile Script Authoring – 20 % Completed
Execute the scripts all at once
Status Cont..
 |  | Total Scripts | Completed Scripts | Remaining Scripts | 
 | Regression - Desktop | 81 | 42 | 39 | 
 | Regression - Mobile | 81 | 14 | 67 | 
 | CSR Orders | 15 | 10 | 5 | 
Status:

## Slide 23: Week 9 : 11th Jan – B2B Automation
Status :
Page Object Capturing – Smoke Scenarios
  Speedo US – Completed
  Speedo Canada – Completed
  Speedo Coaches – Completed
Reusable Script Authoring – Started
  Smoke Pack Scenarios
Next :
Reusable Script Authoring for all other sites
Remaining 3 Sites are not stable in terms of functionalities
  PVH direct
  PVH Corporate Outfitters US
  PVH Corporate Outfitters Canada

## Slide 24: Week 10 : 18th Jan – B2C Automation
Actual Completion :
Page Object Capturing for
  Desktop Browser - 100 % Completed
  Mobile Browser – 65% Completed
Reusable Script Authoring for
  Desktop Browser - 75 % Completed
  Mobile Browser – 38 % Completed
Overall Script Authoring
  Desktop – Completed 43 Scripts Out of 81 – 53 % Completed
  Mobile Site – Completed 14 Script Out of 81 – 17 % Completed
Weekly Task:
  Completion Scripts dry run on PRIMARY PROD Environment
  Started working on adding conditions for Browser & Site Specific Conditions
  Executing Automation Scripts on
    IE 11
    Safari
    Edge Browsers

## Slide 25
Expected Projection for Next Week:
Regression Suite Run for Sprint-4 Execution
Executing Automation Scripts on IE 11, Safari, Edge and Chrome
Adding browser specific functions
Execute all the scripts in 4 Browsers
Status Cont..
 |  | Total Scripts | Completed Scripts | Remaining Scripts | 
 | Regression - Desktop | 66 | 43 | 23 | 
 | Regression - Mobile | 66 | 14 | 52 | 
 | CSR Orders | 15 | 10 | 5 | 
 | Total | 147 | 67 | 70 | 
Status:
Updates and Clarifications:
Last Week Results are updated in OneDrive
Site Slowness and Code Push timelines
Gift Card Details – followup
Open VPN

## Slide 26: Week 10 : 18th Jan – B2B Automation
Status :
Page Object Capturing – Smoke Scenarios
  Speedo US – Completed
  Speedo Canada – Completed
  Speedo Coaches – Completed
  PVH Direct – Completed
  PVH Corporate Outfitter US – Completed
  PVH Corporate Outfitters Canada – Completed
Reusable Script Authoring –
  Smoke Pack Scenarios – 80% Completed
Smoke Pack Script Authoring – Started
  5% Completed
Next :
Continue on Reusable Script Authoring for all other stores
Continue on Smoke Pack Script Authoring for all stores

## Slide 27: Week 11 : 25th Jan – B2C Automation
Actual Completion :
Page Object Capturing for
  Desktop Browser - 100 % Completed
  Mobile Browser – 65% Completed
Reusable Script Authoring for
  Desktop Browser - 75 % Completed
  Mobile Browser – 38 % Completed
Overall Script Authoring
  Desktop – Completed 43 Scripts Out of 81 – 53 % Completed
  Mobile Site – Completed 14 Script Out of 81 – 17 % Completed
Weekly Task:
  Completion Scripts dry run on PRIMARY PROD Environment
  Started working on adding conditions for Browser & Site Specific Conditions
  Executing Automation Scripts on
    IE 11
    Safari
    Edge Browsers

## Slide 28
Expected Projection for Next Week:
Regression Suite Run for Sprint-4 Execution
Executing Automation Scripts on IE 11, Safari, Edge and Chrome
Adding browser specific functions
Execute all the scripts in 4 Browsers
Status Cont..
 |  | Total Scripts | Completed Scripts | Remaining Scripts | 
 | Regression - Desktop | 66 | 43 | 23 | 
 | Regression - Mobile | 66 | 14 | 52 | 
 | CSR Orders | 15 | 10 | 5 | 
 | Total | 147 | 67 | 70 | 
Status:
Updates and Clarifications:
Last Week Results are updated in OneDrive
Site Slowness and Code Push timelines
Gift Card Details – followup
Open VPN

## Slide 29: Week 11 : 25th Jan – B2B Automation
Status :
Page Object Capturing – Smoke Scenarios
  Speedo US – Completed
  Speedo Canada – Completed
  Speedo Coaches – Completed
  PVH Direct – Completed
  PVH Corporate Outfitter US – Completed
  PVH Corporate Outfitters Canada – Completed
Reusable Script Authoring –
  Smoke Pack Scenarios – 80% Completed
Smoke Pack Script Authoring – Started
  5% Completed
Next :
Continue on Reusable Script Authoring for all other stores
Continue on Smoke Pack Script Authoring for all stores

## Slide 30: Week 12 : 31th Jan – B2C Automation
Actual Completion :
Page Object Capturing for
  Desktop Browser - 100 % Completed
  Mobile Browser – 65% Completed
Reusable Script Authoring for
  Desktop Browser - 75 % Completed
  Mobile Browser – 38 % Completed
Overall Script Authoring
  Desktop – Completed 45 Scripts Out of 81 – 55 % Completed
  Mobile Site – Completed 14 Script Out of 81 – 17 % Completed
Weekly Task:
  Completion Scripts dry run on PRIMARY PROD Environment
  Started working on adding conditions for Browser & Site Specific Conditions
  Executing Automation Scripts on
    IE 11
    Safari
    Edge Browsers

## Slide 31
Expected Projection for Next Week:
Regression Suite Run for Sprint-4 Execution
Executing Automation Scripts on IE 11, Safari, Edge and Chrome
Adding browser specific functions
Execute all the scripts in 4 Browsers
Status Cont..
 |  | Total Scripts | Completed Scripts | Remaining Scripts | 
 | Regression - Desktop | 66 | 45 | 23 | 
 | Regression - Mobile | 66 | 14 | 52 | 
 | CSR Orders | 15 | 10 | 5 | 
 | Total | 147 | 67 | 70 | 
Status:
Updates and Clarifications:
Site Slowness and Code Push timelines
Open VPN

## Slide 32: Week 12 : 31th Jan – B2B Automation
Status :
Page Object Capturing – Smoke Scenarios
  Speedo US – Completed
  Speedo Canada – Completed
  Speedo Coaches – Completed
  PVH Direct – Completed
  PVH Corporate Outfitter US – Completed
  PVH Corporate Outfitters Canada – Completed
Reusable Script Authoring –
  Smoke Pack Scenarios – 100% Completed
Smoke Pack Script Authoring – Started
  25% Completed
Next :
Continue on Smoke Pack Script Authoring for all stores