## Sheet1
S.No | Module | Script Number | Scenarios | Script Name | PVH/SP | Smoke | Completed Status
1 | Registration | 1 | Register Hyperlink | 001_NewRegistration | Common | Yes | Completed
|  | 2 | Registration text fields |  | Common | Yes | Completed
|  | 3 | Successful Registration Message |  | Common | Yes | Completed
2 | Forgot Password | 4 | Password Reset | 002_ForgotPasswordFlow | Common | Yes | Completed
3 | Login | 5 | Store Logo Redirection | 003_StoreLogoRedHomePage | Common | Yes | Completed
|  | 6 | Successful Login | 004_UpdateCart | Common | Yes | Completed
4 | Search by PDP | 7 | Style # search |  | Common | Yes | Completed
5 | PDP | 8 | Add Product to Cart |  | Common | Yes | Completed
|  | 9 | Add Multiple Products to Cart |  | Common | Yes | Completed
6 | Checkout | 10 | Update shopping Cart |  | Common | Yes | Completed
|  | 11 | Remove Link in Shopping Cart |  | Common | Yes | Completed
7 | Search Term | 12 | Search Result Validation | 005_SearchResult | Common | Yes | Completed
8 | Save Order | 13 | Save order from cart | 006_SavingOrderfromCart | Common | Yes | Completed
9 | Shipping Address Page | 14 | Edit Shipping Address | 007_ShippingPageFlow | Common | Yes | In Progress
|  | 15 | Add new Shipping Address |  | Common | Yes
10 | Payment Page | 16 | PO number Text box validation | 008_CompleteCheckout | Common | Yes | Completed
|  | 17 | Next Button validation |  | Common | Yes | Completed
11 | Order Confirmation Page | 18 | Order Confirmation Page details |  | Common | Yes | Completed
12 | Order Summary Page | 19 | Edit link validation | 009_EditLink, 010_EditLinkPayment, 011_EditLinkShippingMethod | Common | Yes | Completed
|  | 20 | Process Order button validation | 012_SubmitOrder | Common | Yes | Completed
13 | Saved Order Page | 21 | Saved orders link | 013_OpenSavedOrders | Common | Yes | Completed
|  | 22 | Edit Saved Orders Validation |  | Common | Yes | Completed
|  | 23 | Saved order Checkout |  | Common | Yes | Completed
14 | Contact us | 24 | Speedo Contact us Page validation | 014_SpeedoGuest | SP | Yes | Completed
|  | 25 | Speedo Contact us Footer Validation | 015_SpeedoReg | SP | Yes | Completed
15 | Quick Order | 26 | Speedo Quick Order validation | 016_QuickOrder | SP | Yes | In Progress
16 | Coaches : Viewing Allowances | 27 | Speedo Coaches: Allowances validation | 017_CoachesAllowancesScript | SP Coaches | Yes | Completed