## Summary
Non-HB Automation Script Updates
Release | Total Epic/Defects | Automation Candidate | Non-feasible |  |  |  | Comments
|  |  | UI | Email | Dynamic | Backend
2018-07-12 | 26 | 2 | 4 | 3 | 4 | 9 | 01 - Desktop and 01 - Mobile
2018-07-18 | 51 | - | - | - | - | - | HB Release - No updates require for Non-HB
2018-07-26 | 12 | 1 | 1 | 0 | 1 | 8 | Addressy Feature

## Jul-12
S.No | Issue key | Summary | Status | Comments | Require updates in existing scripts | Automation Comments
1 | B2C18Q2-563 | TH - Product Feed | NO QA |  | No | Backend
2 | B2C18Q2-1416 | DC - TH Registration Page |  | Lower case changes in thanks message | Yes
3 | B2C18Q2-98 | TH - Promotional banner and logo on specific pages | Didn't validate, Data dependency | Promotion banners related | No | UI
4 | B2C18Q2-110 | DC - TH - Fix the spacing for the mobile store selections in the preferences and registration |  | Space between the text and label | Yes | Mobile Specifi Fix
5 | B2C18Q2-1220 | DC - Did not receive welcome email when enrolling in the club | Didn't validate, Data dependency | Email Scenarios | No | Email
6 | B2C18Q2-245 | TH - ADA Audit Remediation Commerce Work | NO QA |  | No | Backend
7 | B2C18Q2-1125 | SEO Enhancements ¦ All Brands - PLP/PDP Updates Phase 2 |  |  | No | Backend
8 | B2C18Q2-528 | CK - Minor UI updates |  | UI Changes | No | UI
9 | B2C18Q2-531 | CK - Welcome E-Mail Overlay Changes (Not Always Promotional) |  | CMC level change for Newsletter Signup overlay | No | Email
10 | B2C18Q2-79 | CKUS / CKCA - Low Stock Indicator |  | Data Specific which ever has the less inventory | No | Dynamic
11 | B2C18Q2-540 | CK - Power Review Email Update | Didn't validate, Data dependency | Power review and email related epic | No | Email
12 | B2C18Q2-162 | CK US/CA - Adobe Test & Target - implement mini data layer - Phase 2 |  |  | No | Backend
13 | B2C18Q2-555 | SP - Promo Messaging on PDP | Didn't validate, Data dependency |  | No | Dynamic
14 | B2C18Q2-1214 | DC - SP: My orders displays paypal text two times in the order details section | Didn't validate, Cannot place order |  | No | UI
15 | B2C18Q2-89 | DC - Update SOLR index to handle unpublished plus size SKU | Didn't validate, Data dependency |  | No | Backend
16 | B2C18Q2-1124 | All Brands - 6/28 Fast follow | Didn't validate, Data dependency |  | No
17 | B2C18Q2-1367 | All Brands - 7/12 Fast follow |  |  | No
18 | B2C18Q2-106 | DC - All brands - Mobile Personal Preference Page & Sign-in autofill | Didn't validate, Data dependency |  | No | Dynamic
19 | B2C18Q2-1653 | 7/12 Release Regression |  |  | No
20 | B2C18Q2-34 | All Brands - Facebook open graph image tag wrong |  |  | No | UI
21 | B2C18Q2-130 | SEO ¦ All Brands - Hidden Categories- Noindex Tag | Didn't validate, Data dependency |  | No | Backend
22 | B2C18Q2-1407 | DC - ApplePay merchant configuration Info should not be looked for stores when ApplePay is disabled |  |  | No | Backend
23 | B2C18Q2-1485 | SEO Enhancements ¦ All Brands - PLP/PDP Updates Phase 3 |  |  | No | Backend
24 | B2C18Q2-1222 | DC - On load of PDP edit overlay, a size change event should not be triggered |  |  | No | Backend
25 | B2C18Q2-1186 | DC - CSR - The Enter Key is not Functional in the CSR App |  |  | No
26 | B2C18Q2-1216 | DC - (Shopping bag page)-On editing the quantity more than the available quantity the error message is not displayed |  |  | No | Dynamic

## Jul-18
S.No. | Issue Type | Issue key | Summary | Priority | JIRA Status | QA Status | Comment
5 | UAT Bug | HB-6121 | SOFT LAUNCH ¦ UI ¦ SEARCH RESULTS ISSUE | Minor | UAT - Business | Pass
6 | UAT Bug | HB-6123 | SOFT LAUNCH ¦ UI ¦ PDP FIT BOXES ISSUE | Minor | UAT - Business | Pass
7 | UAT Bug | HB-6138 | SOFT LAUNCH ¦ UI ¦ PLP SWATCH NAV IS VISIBLE WHEN IT SHOULD NOT BE | Minor | UAT - Business | Pass
8 | UAT Bug | HB-6091 | Returns Confirmation Email ¦ Returns pricing details are not reflecting order confirmation pricing details | Medium | Complete | In progress | Defect B2C18Q2-1875 came to QA
9 | UAT Bug | HB-6128 | SOFT LAUNCH ¦ UI ¦ MOBILE SIZE CHARTS ISSUE | Minor | UAT - Business | Pass
10 | UAT Bug | HB-6111 | soft launch ¦ tie style filter | Minor | UAT - Business | Pass
11 | UAT Bug | HB-6127 | Soft Launch 1 ¦ UI ¦ Mobile - Image zoom is still not hi-res | Medium | UAT - Business | Pass | Lina Yang to review this
12 | UAT Bug | HB-6119 | SOFT LAUNCH ¦ UI ¦ Utility pages image issues | Minor | QA | Pass
13 | UAT Bug | HB-6171 | CK: Account registration page now contains inaccurate info | Major | UAT - Business | Pass
14 | UAT Bug | HB-6207 | soft launch - product images missing in checkout | Critical | UAT-IT | Pass
15 | UAT Bug | HB-6197 | DR1 (S3) - Imaage thumbnails on PDP are not working | Critical | UAT-IT | Pass
16 | UAT Bug | HB-6199 | Soft launch ¦ tie style filter | Minor | Complete | Pass
17 | UAT Bug | HB-6198 | Soft Launch 1 ¦ UI ¦ Mobile - Image zoom is still not hi-res | Medium | Complete | Pass
18 | QA Bug | HB-6107 | PLP: Sort by Top Rated is showing same sequence as Featured | Medium | Complete | Blocked | Nouar and Mahesh Pandey to let us know how to test
19 | QA Bug | HB-6065 | Regression¦SQ2¦Order Confirmation Page¦ close button alignment issue on "Cancel Order" confirmation modal | Minor | Complete | Fail | Comparing to the other overlays the close icon is still misaligned - B2C18Q2-2023
20 | QA Bug | HB-6103 | Quick View ¦ On having tie(item) in the cart we are not able to edit the other products available in the cart | Major | Complete | Pass
21 | QA Bug | HB-6163 | Desktop¦Search Result Page¦All Results coming up in one tab. | Medium | Complete | Pass
22 | QA Bug | HB-6168 | Certona recommandation ¦¦ Size attributes are misaligned in Quick Add of product tile | Minor | Complete | Blocked | Certona issue, B2C18Q2-2038
23 | QA Bug | HB-6162 | Desktop¦ CTA Bar¦Long Product name do not have ellipses. | Minor | Complete | Pass
24 | QA Bug | HB-6185 | SQ2 ¦ PLP ¦ Unable to add "One Size" product to cart after changing the color | Major | Complete | Pass
25 | QA Bug | HB-6188 | SQ2 ¦ Bundle PDP behavior is inconsistent on selecting size attribute. | Medium | Complete | Blocked | Asked Ruchi and Nouar for Bundle products
26 | QA Bug | HB-6157 | SQ2 PDP - product name appears in breadcrumbs | Major | Complete | Pass
27 | QA Bug | HB-6189 | Mobile¦PDP¦Bundle PDP UI issues | Minor | Complete | Blocked | Asked Ruchi and Nouar for Bundle products
28 | QA Bug | HB-6196 | PDP page ¦ Content espot tile ¦ Size container overlapping with buttons when user clicks on quick add button | Minor | Complete | Pass
29 | QA Bug | HB-6183 | SQ2¦Desktop¦Checkout Guest user-Register yourself overlay¦Alignment issues in overlay | Minor | Complete | Pass | Total of 3 scenarios, failing in 1 - created HB-6236/B2C18Q2-2023
30 | QA Bug | HB-6205 | Complete the look product tiles Issues | Major | Complete | Blocked | "Complete the Look" type of products, unsure what these are, asked Ruchi and Nouar
31 | UAT Bug | HB-6126 | SOFT LAUNCH ¦ UI ¦ BREADCRUMBS | Minor | Complete | Pass
32 | UAT Bug | HB-6136 | SOFT LAUNCH ¦ UI ¦ PDP BOTTOM ADD TO BAG BAR ISSUE | Medium | Complete | Pass
33 | UAT Bug | HB-6131 | SOFT LAUNCH ¦ UI ¦ IE 11 MISALIGNED FILTER | Minor | Complete | Pass
34 | UAT Bug | HB-6137 | SOFT LAUNCH ¦ UI ¦ SEARCH ICON MISALIGNED | Minor | Complete | Pass | ie11 - will check later
35 | UAT Bug | HB-6117 | SOFT LAUNCH ¦ UI ¦ Store Locator Breadcrumb issue | Minor | Complete | Blocked | Created new defect B2C18Q2-2019
36 | UAT Bug | HB-6087 | soft launch - rewards error message update | Minor | Complete | Blocked | Have to bring zeta down
37 | UAT Bug | HB-6108 | soft launch - update rewards message in SC | Minor | Complete | Yet to Start
38 | UAT Bug | HB-6154 | soft launch ¦ womens product pdp missing style number and country of origin | Medium | Complete | Pass | Closed defect B2C18Q2-2024
39 | UAT Bug | HB-6133 | SOFT LAUNCH ¦ UI ¦ MAIN NAV UNDERLINES NOT DISPLAYING | Medium | Complete | Pass
40 | UAT Bug | HB-6124 | SOFT LAUNCH ¦ UI ¦ EMPTY SHOPPING BAG MESSAGE ISSUE | Minor | Complete | Pass
41 | UAT Bug | HB-6169 | soft launch - duplicate product name in shopping cart | Critical | Complete | Pass
42 | UAT Bug | HB-6090 | soft launch - modal close button | Minor | Complete | Yet to Start
43 | UAT Bug | HB-5857 | Soft launch - Wrong format on edit overlay in SC | Minor | Complete | Yet to Start
44 | QA Bug | B2C18Q2-1875 | HB - PQ1 - Ship & Return Emails are not getting generated | Major | QA | Fail | Didn’t receive ship confirmation emails
45 | QA Bug | B2C18Q2-2023 | PQ1- HB - The ‘X’ close button in the Cancel Order overlay is misaligned | Minor | Dev Blocked | Not ready for QA
46 | QA Bug | B2C18Q2-2044 | PQ1¦HB: Product part number is inappropriate in tealium while adding to cart from Quick add | Minor | Scope Review | Not ready for QA | New defect created by QA today
47 | QA Bug | B2C18Q2-2043 | PQ1- HB - â€˜All Search Resultsâ€™ tab is showing as a single tab on the Search results page inconsistently | Minor | New | Not ready for QA | New defect created by QA today
48 | QA Bug | B2C18Q2-2041 | PQ1¦HB: Partnumber array is empty while adding to cart from PDP and from add to cart carousal in footer | Minor | Scope Review | Not ready for QA | New defect created by QA today
49 | QA Bug | B2C18Q2-2040 | PQ1- HB - No images are displayed for some products on the Search Results page and the PDP | Minor | Scope Review | Not ready for QA | New defect created by QA today
50 | QA Bug | B2C18Q2-2038 | PQ1- HB - No QV buttons in Certona Recommendations | Minor | New | Not ready for QA | New defect created by QA today
51 | QA Bug | B2C18Q2-2037 | HB¦PQ1: "You may also like" section overlaps with qty dropdown and "Add to bag" button on scrolling | Minor | New | Not ready for QA | New defect created by QA today

## Jul-26
Issue key | Summary | Priority | Status | QA -> UAT Dates | Open Defects | Comments | Require updates in existing scripts | Automation Comments
B2C18Q2-1370 | SEO Enhancements ¦ CK & Speedo¦ Additional Updates | Minor | Regression Testing | 2018-07-12 |  | No Open Defects | No | Backend
B2C18Q2-835 | TH - ADA Audit Remediation 3rd Party Work | Minor | In Production |  |  | General automation is still pending | No | Backend
B2C18Q2-1534 | DC - CSR - Add / Remove CSR Call Tagging | Minor | UAT |  |  | CSR Releated testing and features | No | Backend
B2C18Q2-1458 | Apple Pay Orders State Code fix on Order Transfer job | Major | QA | 2018-07-11 | B2C18Q2-2039 - Blocker - Pending Development | Apple Pay feature and backend testing | No | Backend
B2C18Q2-1746 | 7/26 - Release Regression | Minor | QA | 2018-07-20 | B2C18Q2-2042 - Blocker - Development
B2C18Q2-525 | CK - Ovative Product Feed | Major | QA | 2018-07-13 |  | Infoverity QA will test. No scope for Sirius QA | No | Backend
B2C18Q2-516 | All Brands - Address validation API (Addressy) | Major | QA | 2018-07-12 |  | Addressy was disabled on Friday, we need to do regression to ensure the existing feature is not broken | Yes | Fix required to maintain the existing scripts. No to cover the addressy feature
B2C18Q2-680 | CK Minor UI Updates #2 | Minor | QA | 2018-07-11 |  | Someone modified the epic summary (CK - Alternate images not functioning properly on apparel bundle) and now unable to open the epic due to error | No | UI
B2C18Q2-522 | THCK-Heritage - Exclude Returns Processing Fee From Rakuten Feed | Major | QA | 2018-07-12 |  | eSW issue is fixed. DV2 partner brands ticket is still open | No | Backend
B2C18Q2-1545 | All Brands - 7/26 Fast Follow | Minor | QA | 2018-07-20 | HB-5925 - Major - Scope Review |  | No
B2C18Q2-735 | TH - ADA Audit Remediation Content Work | Minor | Development |  |  | General automation is still pending | No | Backend
B2C18Q2-1350 | TH - ADA Audit Remediation Commerce Work Phase II | Major | UAT |  |  | No_QA | No | Backend
B2C18Q2-538 | TH - US Tommy eCommerce - Site Filter Enhancements | Major | QA | 2018-07-12 | B2C18Q2-2088 - Minor - QA | Nachi, not sure who pushed this defect to B2C18Q2-2073 fast follow epic? | No | Dynamic
B2C18Q2-2052 - Minor - QA
B2C18Q2-2052 - Minor - QA
B2C18Q2-2051 - Minor - QA